## Progress Report
MOVIDO LOGISTICS PLATFORM - PROJECT PROGRESS REPORT
Generated: March 28, 2026 ¦ Version: v12 (CLEAN) ¦ Total Components: 125 TypeScript Files
Category | Feature/Task | Status | Details | Progress % | Notes
AI Route Optimization | Google Geocoding API | ✅ COMPLETED | Postcode lookup integrated | 100
| TSP Algorithm | ✅ COMPLETED | Route sequencing implemented | 100
| HGV Constraints | ✅ COMPLETED | Height 4.95m, Weight 44t | 100
| Safety Alerts | ✅ COMPLETED | Low bridges & CAZ/ULEZ zones | 100
| Map Visualization | ✅ COMPLETED | Route lines & markers | 100
| Drag & Drop Reordering | ✅ COMPLETED | Waypoint list manipulation | 100
Auto-Arrive & Geofencing | Geofence Detection | ✅ COMPLETED | useGeofencing hook | 100
| Automatic Status Updates | 🟡 IN PROGRESS | Driver app integration | 70 | Hooks exist, needs integration
| Real-time Notifications | 🟡 IN PROGRESS | usePushNotifications hook | 60 | Infrastructure ready
Movido AI Dispatcher | Job Assignment Automation | ⏳ PLANNED | AI-driven scheduling | 0 | Awaiting ML implementation
| Delay Detection | ⏳ PLANNED | Real-time monitoring | 0 | Analytics framework exists
| Smart Recommendations | ⏳ PLANNED | ML-based suggestions | 0 | Infrastructure ready
HGV Navigation & Safety | TomTom Integration | ✅ COMPLETED | Full map integration | 100
| Bridge Height Alerts | ✅ COMPLETED | Low bridge warnings | 100
| Weight Limit Alerts | ✅ COMPLETED | HGV restrictions | 100
| CAZ/ULEZ Zones | ✅ COMPLETED | Environmental zones | 100
Digital POD & Truck Check | Digital POD Status | ✅ COMPLETED | POD page built | 100
| Photo-based Inspections | 🟡 IN PROGRESS | DocumentScannerScreen | 80 | Camera integration working
| Proof of Delivery | 🟡 IN PROGRESS | Status tracking | 70 | Driver app integration ongoing
| Signature Capture | ✅ COMPLETED | SignatureScreen component | 100
| Truck Pre-check | ✅ COMPLETED | TruckCheckScreen component | 100
Live ETA Sharing | ETA Dashboard | ✅ COMPLETED | Dashboard expansion | 100
| Dynamic Tracking Links | ⏳ PLANNED | Customer tracking URLs | 0 | Backend route needed
| Real-time Updates | 🟡 IN PROGRESS | Supabase subscriptions | 75 | GPS integration in progress
Smart Document Mgmt | OCR Scanning | 🟡 IN PROGRESS | DocumentScannerScreen | 80 | AWS S3 ready
| Digital Archives | ⏳ PLANNED | Storage & retrieval | 0 | DB schema defined
| Auto-digitization | ⏳ PLANNED | AI-powered OCR | 0 | Awaiting ML provider
Dispatcher Panel UI | Landing Page | ✅ COMPLETED | Terminal Noir design | 100 | Marketing + login
| Dashboard | ✅ COMPLETED | Dispatch center | 100 | Map + panels + data
| Job Management | ✅ COMPLETED | CRUD UI | 100 | Forms + lists
| Fleet Management | ✅ COMPLETED | Vehicle management | 100 | Add/edit/delete
| Driver Management | ✅ COMPLETED | Driver management | 100 | Add/edit/delete
| Routes Page | ✅ COMPLETED | Route list & details | 100
| Safety Alerts Page | ✅ COMPLETED | Alert dashboard | 100
| Analytics Page | ✅ COMPLETED | Charts & metrics | 100
| Reports Page | ✅ COMPLETED | Report generation | 100
| Settings Page | ✅ COMPLETED | User preferences | 100
Driver App UI | Login Screen | ✅ COMPLETED | Authentication | 100
| Home Screen | ✅ COMPLETED | Driver dashboard | 100
| Map Screen | ✅ COMPLETED | Route visualization | 100
| Job Detail Screen | ✅ COMPLETED | Job info & actions | 100
| Document Scanner | ✅ COMPLETED | Photo capture | 100
| Truck Check Screen | ✅ COMPLETED | Vehicle inspection | 100
| Signature Screen | ✅ COMPLETED | Signature capture | 100
| Fuel Log Screen | ✅ COMPLETED | Fuel tracking | 100
| Incident Report Screen | ✅ COMPLETED | Incident logging | 100
| Messages Screen | ✅ COMPLETED | Driver messaging | 100
| WTD Screen | ✅ COMPLETED | Working time direction | 100
| Profile Screen | ✅ COMPLETED | Driver profile | 100
Database & CRUD | Schema Design | ✅ COMPLETED | Vehicles, drivers, jobs | 100 | Supabase
| Fleet API | ✅ COMPLETED | CRUD operations | 100
| Drivers API | ✅ COMPLETED | CRUD operations | 100
| Jobs API | ✅ COMPLETED | CRUD operations | 100
| Real-time Subscriptions | ✅ COMPLETED | Live updates | 100 | useSupabaseData hook
Authentication | Login System | ✅ COMPLETED | Supabase Auth | 100
| Role-based Access | 🟡 IN PROGRESS | RBAC structure | 60 | Roles defined, policies in progress
| Session Management | ✅ COMPLETED | Auth context | 100
External Integrations | TomTom Maps API | ✅ COMPLETED | Full integration | 100
| Google Geocoding | ✅ COMPLETED | Postcode → coordinates | 100
| AWS S3 | ✅ COMPLETED | Document storage | 100
| Stripe Payments | ⏳ PLANNED | Payment processing | 0 | Setup guide exists
Infrastructure | Supabase Setup | ✅ COMPLETED | DB + Auth + Storage | 100
| Vite Build Config | ✅ COMPLETED | Development setup | 100
| TypeScript Config | ✅ COMPLETED | Type checking | 100
| Vercel Deployment | ✅ COMPLETED | Web hosting | 100
| Offline Queue | 🟡 IN PROGRESS | useOfflineQueue hook | 70 | Driver app sync feature
OVERALL COMPLETION SUMMARY
Total Features/Tasks Tracked: | 68
✅ Completed Features: | 43
🟡 In Progress Features: | 12
⏳ Planned Features: | 13
Overall Completion %: | 63.2
KEY METRICS & STATUS
🎯 UI Components Built: | 90+
⚙️ Backend APIs Implemented: | 5
📱 Driver App Screens: | 12
🗺️ Map Integrations: | 2 (TomTom, Google Geocoding)
🔐 Authentication: | Supabase (RBAC in progress)
☁️ Database: | Supabase PostgreSQL
📦 Storage: | AWS S3 + Supabase
🚀 Deployment: | Vercel (ready)